**Template Action Plan: Renewing the Covenant in the Capital**

**Aim**

To train and prepare staff to enable the Borough Council to meet its Armed Forces Covenant obligations:

**Objectives**

* To ensure all policies are reviewed and adjusted accordingly to deliver our commitment to the Armed Forces Covenant (AFC)
* To deliver a training programme for managers and Armed Forces Champions in the Council, specifically those who have responsibility for main Covenant policy areas
* To deliver ongoing awareness training to all frontline staff and Councillors to enable them to ‘ask the question’ when engaging with residents
* To establish an AFC partnership meeting with relevant stakeholders
* To renew our commitment to the Armed Forces Community by re-signing the AFC

**Benefits**

* Public awareness of the commitment / support provided by the council to an under-represented community group (~10-15% of the population)
* Continuous Professional Development for staff
* Reduced (or at the very least, shared) burden of service provision through use of support pathways and external providers
* Improved customer satisfaction through knowledgeable customer service of how to support / signpost Armed Forces community (via training, e-learning and signposting app).
* Gain a better understanding of local demographics by staff regularly “asking the question” and recording how many of this community are accessing services.
* Improved visibility and reputation as a ‘forces friendly’ employer through the Employer Recognition Scheme. Gain benefits of employing service leavers and reservists.
* Closer partnership working with neighbouring Boroughs and military stakeholders to potentially reduce burden of support and avoid duplication of effort on events or community initiatives.

**Timeline**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Action** | **Description** | **Stakeholders** |
| ASAP | Armed Forces Champion Approval | Discussion with HQ London District and Council Armed Forces Champion to look at military footprint, local need, what project can deliver and benefits to council | HQ London District Council Armed Forces Champion |
| + 1 week | Approval | Project approved/rejected | Council Armed Forces Champion |
| + 1 month | Meet with Senior Managers to outline the proposal in more detail | Discuss in more detail how to deliver this initiative across the council.Discussions to include policy reviews, training of both senior managers and frontline staff, installation of e-learning package, establishment of partnership meetings and re-signing AFC | HQ London District Council Armed Forces ChampionCouncillor Armed Forces ChampionChief Executive OfficerLeader of the CouncilCouncil Policy LeadCouncil Training LeadCouncil Communications Lead |
| + 2 months | Deliver senior training | Deliver two-hour training to Armed Forces Champions, senior staff, department leads and line managers to upskill them on the AFC, the unique needs / issues of Armed Forces Community and how their staff can support. | HQ London District Council Armed Forces ChampionCouncillor Armed Forces ChampionExtended Leadership TeamLine Management Team |
| + 3 months | Deliver frontline staff training | Hold multiple 1-hour training events to upskill as many frontline staff as possible. | HQ London District Frontline Staff |
| + 3 months | Launch e-learning package | Install e-learning package into Learning Management System, roll out to frontline staff who interact directly with residents and then wider council staff for awareness | HQ London District Council Training Lead |
| Any time | Review Employer Recognition Scheme (ERS) Status | Review status of council as an employer from Armed Forces Community. As a signatory of AFC you can self-nominate for Bronze ERS Award via Greater London Reserve Forces and Cadet Association (GL RFCA). If already held, review next steps to progress to Silver / Gold.Presentation of award to CEO / Councillors can be arranged | Council Armed Forces ChampionHQ London District GL RFCA |
| + 3 months | Re-sign AFC | Organise a re-signing of AFC by council with local Military Leaders with a renewed and developed action plan in place to publicly deliver that commitmentPotential to combine with presentation of ERS Award | HQ London DistrictCouncil Armed Forces ChampionCouncillor Armed Forces ChampionSenior Management TeamMayorCouncil Communications LeadLocal Military UnitsGL RFCALocal military partners / charities |
| + 6 months(and ongoing) | AFC Partnership Meeting | Partnership meeting to be facilitated by HQ London District to: 1. Review council commitment to AFC
2. Understand any issues raised since start of initiative
3. Discuss best practice with partner organisations
4. Plan and deconflict events with local military units / neighbouring Borough Councils
5. Build relationships for collaborative working

Standing agenda to be provided to ensure continuity and consistency for future meetings | HQ London DistrictCouncil Armed Forces ChampionCouncillor Armed Forces ChampionLocal Military UnitsPartner Organisations  |
| Ongoing | Sustainable awareness training | Embed e-learning package into new joiners routine and regular annual online trainingFrontline staff training package to be provided for service heads / line managers / Armed Forces Champion to be able to deliver to staff on an ongoing basis | HQ London District Council Armed Forces ChampionTraining Lead |